## Gantt
Boards - Resalat Bank Wallet (by quarters)
|  |  | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025
| Start | End | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Requirements Gathering | 04-May-2024 | 08-May-2024 | May: Requirements Gathering (04-May-24 - 08-May-24)
Conduct stakeholder meetings to collect detailed requirements | 04-May-2024 | 05-May-2024 | May: Conduct stakeholder meetings to collect detailed requirements (04-May-24 - 05-May-24)
Document and organize requirements | 05-May-2024 | 05-May-2024 | May: Document and organize requirements (05-May-24 - 05-May-24)
Document Scopes | 06-May-2024 | 06-May-2024 | May: Document Scopes (06-May-24 - 06-May-24)
Conduct feasibility study | 07-May-2024 | 07-May-2024 | May: Conduct feasibility study (07-May-24 - 07-May-24)
Requirements Validation and Confirmation | 08-May-2024 | 08-May-2024 | May: Requirements Validation and Confirmation (08-May-24 - 08-May-24)
Research on similar NLP models available | 05-May-2024 | 09-May-2024 | May: Research on similar NLP models available (05-May-24 - 09-May-24)
UX/UI Research and Evaluation | 05-May-2024 | 09-May-2024 | May: UX/UI Research and Evaluation (05-May-24 - 09-May-24)
Identify and analyze similar products | 05-May-2024 | 06-May-2024 | May: Identify and analyze similar products (05-May-24 - 06-May-24)
Conduct detailed UX/UI evaluations | 07-May-2024 | 09-May-2024 | May: Conduct detailed UX/UI evaluations (07-May-24 - 09-May-24)
Schedule project timeline | 11-May-2024 | 12-May-2024 | May: Schedule project timeline (11-May-24 - 12-May-24)
Prepare and implement a prototype based on requirements | 11-May-2024 | 25-May-2024 | May: Prepare and implement a prototype based on requirements (11-May-24 - 25-May-24)
Design app architecture for scalability | 11-May-2024 | 20-May-2024 | May: Design app architecture for scalability (11-May-24 - 20-May-24)
Data collection | 11-May-2024 | 15-May-2024 | May: Data collection (11-May-24 - 15-May-24)
Risk analysis | 13-May-2024 | 14-May-2024 | May: Risk analysis (13-May-24 - 14-May-24)
Hold stakeholder meetings for feedback | 15-May-2024 | 15-May-2024 | May: Hold stakeholder meetings for feedback (15-May-24 - 15-May-24)
Document new requirements | 16-May-2024 | 16-May-2024 | May: Document new requirements (16-May-24 - 16-May-24)
Develop acceptance criteria | 17-May-2024 | 17-May-2024 | May: Develop acceptance criteria (17-May-24 - 17-May-24)
Hold meeting with development team for new requirements | 18-May-2024 | 18-May-2024 | May: Hold meeting with development team for new requirements (18-May-24 - 18-May-24)
Data storage and management | 18-May-2024 | 25-May-2024 | May: Data storage and management (18-May-24 - 25-May-24)
Add some functionality to prototype and transition screen | 21-May-2024 | 25-May-2024 | May: Add some functionality to prototype and transition screen (21-May-24 - 25-May-24)
Prioritize backlogs | 25-May-2024 | 28-May-2024 | May: Prioritize backlogs (25-May-24 - 28-May-24)
Update prototype based on new requirements | 25-May-2024 | 08-Jun-2024 | May: Update prototype based on new requirements (25-May-24 - 08-Jun-24); Jun: Update prototype based on new requirements (25-May-24 - 08-Jun-24)
Set up initial database structures | 25-May-2024 | 29-May-2024 | May: Set up initial database structures (25-May-24 - 29-May-24)
Development Environment Setup | 25-May-2024 | 29-May-2024 | May: Development Environment Setup (25-May-24 - 29-May-24)
Configure Development Tools and Environments | 25-May-2024 | 27-May-2024 | May: Configure Development Tools and Environments (25-May-24 - 27-May-24)
Set up Git Version Control | 27-May-2024 | 29-May-2024 | May: Set up Git Version Control (27-May-24 - 29-May-24)
Create Special APIs | 29-May-2024 | 08-Jun-2024 | May: Create Special APIs (29-May-24 - 08-Jun-24); Jun: Create Special APIs (29-May-24 - 08-Jun-24)
Sync with Resalat Bank API | 30-May-2024 | 02-Jun-2024 | May: Sync with Resalat Bank API (30-May-24 - 02-Jun-24); Jun: Sync with Resalat Bank API (30-May-24 - 02-Jun-24)
Assist in testing the prototype | 01-Jun-2024 | 08-Jun-2024 | Jun: Assist in testing the prototype (01-Jun-24 - 08-Jun-24)
Create Unit tests on API | 02-Jun-2024 | 08-Jun-2024 | Jun: Create Unit tests on API (02-Jun-24 - 08-Jun-24)
Data Preprocessing | 08-Jun-2024 | 22-Jun-2024 | Jun: Data Preprocessing (08-Jun-24 - 22-Jun-24)
Data Cleaning | 08-Jun-2024 | 10-Jun-2024 | Jun: Data Cleaning (08-Jun-24 - 10-Jun-24)
Noise Reduction | 11-Jun-2024 | 12-Jun-2024 | Jun: Noise Reduction (11-Jun-24 - 12-Jun-24)
Data Normalization | 15-Jun-2024 | 17-Jun-2024 | Jun: Data Normalization (15-Jun-24 - 17-Jun-24)
Feature Extraction | 18-Jun-2024 | 19-Jun-2024 | Jun: Feature Extraction (18-Jun-24 - 19-Jun-24)
Text to Vector Conversion | 20-Jun-2024 | 22-Jun-2024 | Jun: Text to Vector Conversion (20-Jun-24 - 22-Jun-24)
SMS Verification API Integration | 08-Jun-2024 | 10-Jun-2024 | Jun: SMS Verification API Integration (08-Jun-24 - 10-Jun-24)
User Authentication Service | 08-Jun-2024 | 11-Jun-2024 | Jun: User Authentication Service (08-Jun-24 - 11-Jun-24)
Registration Form | 08-Jun-2024 | 12-Jun-2024 | Jun: Registration Form (08-Jun-24 - 12-Jun-24)
Login/Password Recovery Form | 08-Jun-2024 | 12-Jun-2024 | Jun: Login/Password Recovery Form (08-Jun-24 - 12-Jun-24)
Backlog Monitoring | 08-Jun-2024 | 10-Jun-2024 | Jun: Backlog Monitoring (08-Jun-24 - 10-Jun-24)
OTP Service Implementation | 11-Jun-2024 | 12-Jun-2024 | Jun: OTP Service Implementation (11-Jun-24 - 12-Jun-24)
Project Progress Oversight | 11-Jun-2024 | 16-Jun-2024 | Jun: Project Progress Oversight (11-Jun-24 - 16-Jun-24)
Session Management Service | 12-Jun-2024 | 16-Jun-2024 | Jun: Session Management Service (12-Jun-24 - 16-Jun-24)
Create & Execute Unit Tests | 15-Jun-2024 | 19-Jun-2024 | Jun: Create & Execute Unit Tests (15-Jun-24 - 19-Jun-24)
Security Question Form (KAPCHA) | 15-Jun-2024 | 22-Jun-2024 | Jun: Security Question Form (KAPCHA) (15-Jun-24 - 22-Jun-24)
Create & Execute Responsivity Testing | 15-Jun-2024 | 22-Jun-2024 | Jun: Create & Execute Responsivity Testing (15-Jun-24 - 22-Jun-24)
Scope Updates | 16-Jun-2024 | 22-Jun-2024 | Jun: Scope Updates (16-Jun-24 - 22-Jun-24)
RNN Architecture Design | 23-Jun-2024 | 06-Jul-2024 | Jun: RNN Architecture Design (23-Jun-24 - 06-Jul-24); Jul: RNN Architecture Design (23-Jun-24 - 06-Jul-24)
Sequence Padding | 23-Jun-2024 | 26-Jun-2024 | Jun: Sequence Padding (23-Jun-24 - 26-Jun-24)
Embedding Layer | 29-Jun-2024 | 06-Jul-2024 | Jun: Embedding Layer (29-Jun-24 - 06-Jul-24); Jul: Embedding Layer (29-Jun-24 - 06-Jul-24)
Registration Backend Implementation | 23-Jun-2024 | 29-Jun-2024 | Jun: Registration Backend Implementation (23-Jun-24 - 29-Jun-24)
Login/Password Recovery Backend | 23-Jun-2024 | 26-Jun-2024 | Jun: Login/Password Recovery Backend (23-Jun-24 - 26-Jun-24)
User Account Dashboard | 23-Jun-2024 | 06-Jul-2024 | Jun: User Account Dashboard (23-Jun-24 - 06-Jul-24); Jul: User Account Dashboard (23-Jun-24 - 06-Jul-24)
Responsivity Testing | 23-Jun-2024 | 06-Jul-2024 | Jun: Responsivity Testing (23-Jun-24 - 06-Jul-24); Jul: Responsivity Testing (23-Jun-24 - 06-Jul-24)
Backlog Monitoring | 23-Jun-2024 | 29-Jun-2024 | Jun: Backlog Monitoring (23-Jun-24 - 29-Jun-24)
Logout Backend | 29-Jun-2024 | 02-Jul-2024 | Jun: Logout Backend (29-Jun-24 - 02-Jul-24); Jul: Logout Backend (29-Jun-24 - 02-Jul-24)
Registration Unit Testing | 30-Jun-2024 | 06-Jul-2024 | Jun: Registration Unit Testing (30-Jun-24 - 06-Jul-24); Jul: Registration Unit Testing (30-Jun-24 - 06-Jul-24)
Project Progress Oversight | 30-Jun-2024 | 06-Jul-2024 | Jun: Project Progress Oversight (30-Jun-24 - 06-Jul-24); Jul: Project Progress Oversight (30-Jun-24 - 06-Jul-24)
Login/Logout Unit Testing | 03-Jul-2024 | 06-Jul-2024 | Jul: Login/Logout Unit Testing (03-Jul-24 - 06-Jul-24)
RNN Architecture Refinement | 07-Jul-2024 | 21-Jul-2024 | Jul: RNN Architecture Refinement (07-Jul-24 - 21-Jul-24)
RNN Layer Implementation | 07-Jul-2024 | 13-Jul-2024 | Jul: RNN Layer Implementation (07-Jul-24 - 13-Jul-24)
Dense Layers | 14-Jul-2024 | 15-Jul-2024 | Jul: Dense Layers (14-Jul-24 - 15-Jul-24)
Architecture Review and Optimization | 16-Jul-2024 | 21-Jul-2024 | Jul: Architecture Review and Optimization (16-Jul-24 - 21-Jul-24)
Account Dashboard Backend | 07-Jul-2024 | 15-Jul-2024 | Jul: Account Dashboard Backend (07-Jul-24 - 15-Jul-24)
Account Management Backend (Transaction History and Balance) | 07-Jul-2024 | 15-Jul-2024 | Jul: Account Management Backend (Transaction History and Balance) (07-Jul-24 - 15-Jul-24)
User Account Management Frontend | 07-Jul-2024 | 15-Jul-2024 | Jul: User Account Management Frontend (07-Jul-24 - 15-Jul-24)
Backlog Monitoring | 07-Jul-2024 | 15-Jul-2024 | Jul: Backlog Monitoring (07-Jul-24 - 15-Jul-24)
Account Dashboard Unit Testing | 16-Jul-2024 | 21-Jul-2024 | Jul: Account Dashboard Unit Testing (16-Jul-24 - 21-Jul-24)
Account Management Unit Testing (Transaction History and Balance) | 16-Jul-2024 | 21-Jul-2024 | Jul: Account Management Unit Testing (Transaction History and Balance) (16-Jul-24 - 21-Jul-24)
Responsivity Testing | 16-Jul-2024 | 21-Jul-2024 | Jul: Responsivity Testing (16-Jul-24 - 21-Jul-24)
Project Progress Oversight | 16-Jul-2024 | 21-Jul-2024 | Jul: Project Progress Oversight (16-Jul-24 - 21-Jul-24)
Model Training | 22-Jul-2024 | 05-Aug-2024 | Jul: Model Training (22-Jul-24 - 05-Aug-24); Aug: Model Training (22-Jul-24 - 05-Aug-24)
Optimization Algorithm Selection | 22-Jul-2024 | 24-Jul-2024 | Jul: Optimization Algorithm Selection (22-Jul-24 - 24-Jul-24)
Model Parameter Tuning | 27-Jul-2024 | 30-Jul-2024 | Jul: Model Parameter Tuning (27-Jul-24 - 30-Jul-24)
Objective Function Definition | 31-Jul-2024 | 02-Aug-2024 | Jul: Objective Function Definition (31-Jul-24 - 02-Aug-24); Aug: Objective Function Definition (31-Jul-24 - 02-Aug-24)
Unit Testing | 03-Aug-2024 | 05-Aug-2024 | Aug: Unit Testing (03-Aug-24 - 05-Aug-24)
Money Transfer Backend | 22-Jul-2024 | 30-Jul-2024 | Jul: Money Transfer Backend (22-Jul-24 - 30-Jul-24)
Account Management Backend (Account Information Editing and Security Settings) | 22-Jul-2024 | 30-Jul-2024 | Jul: Account Management Backend (Account Information Editing and Security Settings) (22-Jul-24 - 30-Jul-24)
Money Transfer UI | 22-Jul-2024 | 05-Aug-2024 | Jul: Money Transfer UI (22-Jul-24 - 05-Aug-24); Aug: Money Transfer UI (22-Jul-24 - 05-Aug-24)
Bill Payment and Auto-Pay | 22-Jul-2024 | 28-Jul-2024 | Jul: Bill Payment and Auto-Pay (22-Jul-24 - 28-Jul-24)
Demo and Feedback Gathering | 22-Jul-2024 | 27-Jul-2024 | Jul: Demo and Feedback Gathering (22-Jul-24 - 27-Jul-24)
Acceptance Testing with Stakeholders | 28-Jul-2024 | 31-Jul-2024 | Jul: Acceptance Testing with Stakeholders (28-Jul-24 - 31-Jul-24)
Responsivity Testing | 29-Jul-2024 | 05-Aug-2024 | Jul: Responsivity Testing (29-Jul-24 - 05-Aug-24); Aug: Responsivity Testing (29-Jul-24 - 05-Aug-24)
Money Transfer Unit Testing | 31-Jul-2024 | 05-Aug-2024 | Jul: Money Transfer Unit Testing (31-Jul-24 - 05-Aug-24); Aug: Money Transfer Unit Testing (31-Jul-24 - 05-Aug-24)
Account Management Unit Testing (Account Information Editing and Security Settings) | 31-Jul-2024 | 05-Aug-2024 | Jul: Account Management Unit Testing (Account Information Editing and Security Settings) (31-Jul-24 - 05-Aug-24); Aug: Account Management Unit Testing (Account Information Editing and Security Settings) (31-Jul-24 - 05-Aug-24)
Scope Updates | 01-Aug-2024 | 05-Aug-2024 | Aug: Scope Updates (01-Aug-24 - 05-Aug-24)
Model Evaluation and Testing | 06-Aug-2024 | 20-Aug-2024 | Aug: Model Evaluation and Testing (06-Aug-24 - 20-Aug-24)
Precision-Recall Analysis | 06-Aug-2024 | 20-Aug-2024 | Aug: Precision-Recall Analysis (06-Aug-24 - 20-Aug-24)
Bill Payment, Auto-Pay, and Wallet Top-Up Backend | 06-Aug-2024 | 13-Aug-2024 | Aug: Bill Payment, Auto-Pay, and Wallet Top-Up Backend (06-Aug-24 - 13-Aug-24)
Special Offers and Store Discounts Backend | 06-Aug-2024 | 13-Aug-2024 | Aug: Special Offers and Store Discounts Backend (06-Aug-24 - 13-Aug-24)
Wallet Top-Up UI | 06-Aug-2024 | 20-Aug-2024 | Aug: Wallet Top-Up UI (06-Aug-24 - 20-Aug-24)
Special Offers and Store Discounts UI | 06-Aug-2024 | 13-Aug-2024 | Aug: Special Offers and Store Discounts UI (06-Aug-24 - 13-Aug-24)
Backlog Monitoring | 06-Aug-2024 | 13-Aug-2024 | Aug: Backlog Monitoring (06-Aug-24 - 13-Aug-24)
Bill Payment, Auto-Pay, and Wallet Top-Up Unit Testing | 14-Aug-2024 | 20-Aug-2024 | Aug: Bill Payment, Auto-Pay, and Wallet Top-Up Unit Testing (14-Aug-24 - 20-Aug-24)
Special Offers and Store Discounts Unit Testing | 14-Aug-2024 | 20-Aug-2024 | Aug: Special Offers and Store Discounts Unit Testing (14-Aug-24 - 20-Aug-24)
Responsivity Testing | 14-Aug-2024 | 20-Aug-2024 | Aug: Responsivity Testing (14-Aug-24 - 20-Aug-24)
Project Progress Oversight | 14-Aug-2024 | 20-Aug-2024 | Aug: Project Progress Oversight (14-Aug-24 - 20-Aug-24)
Model Deployment | 21-Aug-2024 | 30-Aug-2024 | Aug: Model Deployment (21-Aug-24 - 30-Aug-24)
Model Serialization | 21-Aug-2024 | 24-Aug-2024 | Aug: Model Serialization (21-Aug-24 - 24-Aug-24)
Security Measures | 25-Aug-2024 | 27-Aug-2024 | Aug: Security Measures (25-Aug-24 - 27-Aug-24)
Model Deployment | 28-Aug-2024 | 30-Aug-2024 | Aug: Model Deployment (28-Aug-24 - 30-Aug-24)
AI API Development | 21-Aug-2024 | 30-Aug-2024 | Aug: AI API Development (21-Aug-24 - 30-Aug-24)
End-to-End Testing | 21-Aug-2024 | 04-Sep-2024 | Aug: End-to-End Testing (21-Aug-24 - 04-Sep-24); Sep: End-to-End Testing (21-Aug-24 - 04-Sep-24)
AI Chat Interface | 21-Aug-2024 | 04-Sep-2024 | Aug: AI Chat Interface (21-Aug-24 - 04-Sep-24); Sep: AI Chat Interface (21-Aug-24 - 04-Sep-24)
Responsivity Testing | 21-Aug-2024 | 04-Sep-2024 | Aug: Responsivity Testing (21-Aug-24 - 04-Sep-24); Sep: Responsivity Testing (21-Aug-24 - 04-Sep-24)
Launch Preparation | 21-Aug-2024 | 04-Sep-2024 | Aug: Launch Preparation (21-Aug-24 - 04-Sep-24); Sep: Launch Preparation (21-Aug-24 - 04-Sep-24)
Finalize Marketing and Launch Plans | 21-Aug-2024 | 26-Aug-2024 | Aug: Finalize Marketing and Launch Plans (21-Aug-24 - 26-Aug-24)
Ensure Documentation Readiness | 27-Aug-2024 | 31-Aug-2024 | Aug: Ensure Documentation Readiness (27-Aug-24 - 31-Aug-24)
Prepare Support Documents for Delivery Package | 01-Sep-2024 | 04-Sep-2024 | Sep: Prepare Support Documents for Delivery Package (01-Sep-24 - 04-Sep-24)
Integration Testing | 31-Aug-2024 | 04-Sep-2024 | Aug: Integration Testing (31-Aug-24 - 04-Sep-24); Sep: Integration Testing (31-Aug-24 - 04-Sep-24)
AI API Unit Testing | 31-Aug-2024 | 04-Sep-2024 | Aug: AI API Unit Testing (31-Aug-24 - 04-Sep-24); Sep: AI API Unit Testing (31-Aug-24 - 04-Sep-24)
Model Maintenance and Updates | 05-Sep-2024 | 19-Sep-2024 | Sep: Model Maintenance and Updates (05-Sep-24 - 19-Sep-24)
Versioning and Updating | 13-Aug-2024 | 19-Aug-2024 | Aug: Versioning and Updating (13-Aug-24 - 19-Aug-24)
Monitoring and Logging | 05-Sep-2024 | 12-Sep-2024 | Sep: Monitoring and Logging (05-Sep-24 - 12-Sep-24)
Final Refinements and QA | 05-Sep-2024 | 19-Sep-2024 | Sep: Final Refinements and QA (05-Sep-24 - 19-Sep-24)
o Implement changes based on testing feedback | 05-Sep-2024 | 12-Sep-2024 | Sep: o Implement changes based on testing feedback (05-Sep-24 - 12-Sep-24)
Feature & Function Ensurance | 13-Sep-2024 | 19-Sep-2024 | Sep: Feature & Function Ensurance (13-Sep-24 - 19-Sep-24)
Final QA and Bug Fixes | 05-Sep-2024 | 19-Sep-2024 | Sep: Final QA and Bug Fixes (05-Sep-24 - 19-Sep-24)
Conduct thorough QA testing | 05-Sep-2024 | 14-Sep-2024 | Sep: Conduct thorough QA testing (05-Sep-24 - 14-Sep-24)
Fix any remaining bugs or issues | 15-Sep-2024 | 19-Sep-2024 | Sep: Fix any remaining bugs or issues (15-Sep-24 - 19-Sep-24)
AI Chat Interface | 05-Sep-2024 | 19-Sep-2024 | Sep: AI Chat Interface (05-Sep-24 - 19-Sep-24)
Responsivity Testing | 05-Sep-2024 | 19-Sep-2024 | Sep: Responsivity Testing (05-Sep-24 - 19-Sep-24)
Setup meeting with stakeholders for launch | 05-Sep-2024 | 19-Sep-2024 | Sep: Setup meeting with stakeholders for launch (05-Sep-24 - 19-Sep-24)
Final Refinements | 20-Sep-2024 | 30-Sep-2024 | Sep: Final Refinements (20-Sep-24 - 30-Sep-24)
Final Touches | 20-Sep-2024 | 11-Oct-2024 | Sep: Final Touches (20-Sep-24 - 11-Oct-24); Oct: Final Touches (20-Sep-24 - 11-Oct-24)
Stakeholder Launch Meeting | 20-Sep-2024 | 11-Oct-2024 | Sep: Stakeholder Launch Meeting (20-Sep-24 - 11-Oct-24); Oct: Stakeholder Launch Meeting (20-Sep-24 - 11-Oct-24)
Feature Validation | 01-Oct-2024 | 05-Oct-2024 | Oct: Feature Validation (01-Oct-24 - 05-Oct-24)
QA Testing | 06-Oct-2024 | 08-Oct-2024 | Oct: QA Testing (06-Oct-24 - 08-Oct-24)
Bug Fixes | 09-Oct-2024 | 11-Oct-2024 | Oct: Bug Fixes (09-Oct-24 - 11-Oct-24)
Launch | 12-Oct-2024 | 20-Oct-2024 | Oct: Launch (12-Oct-24 - 20-Oct-24)
Collect Deploy the app | 12-Oct-2024 | 14-Oct-2024 | Oct: Collect Deploy the app (12-Oct-24 - 14-Oct-24)
Monitor initial user feedback and performance | 15-Oct-2024 | 20-Oct-2024 | Oct: Monitor initial user feedback and performance (15-Oct-24 - 20-Oct-24)
Post-Launch Support | 21-Oct-2024 | 31-Oct-2024 | Oct: Post-Launch Support (21-Oct-24 - 31-Oct-24)
Provide immediate support for any critical issues | 21-Oct-2024 | 26-Oct-2024 | Oct: Provide immediate support for any critical issues (21-Oct-24 - 26-Oct-24)
Plan for future updates and enhancements based on user feedback | 27-Oct-2024 | 31-Oct-2024 | Oct: Plan for future updates and enhancements based on user feedback (27-Oct-24 - 31-Oct-24)